## Contacts
Name | Email | Phone | Personal email | GitHub
Jeff Janes | jeff308@revature.net | 925.699.7918 | jjanes0918@gmail.com | https://github.com/JeffJanes2023
Nicholas Kroeger | nicholas537@revature.net | (203) 917-5168 | nrkroeger1@gmail.com | github.com/NRKroeger
Parker Van Every | parker954@revature.net | (619) 750-4673 | pdvanevery@gmail.com | https://github.com/pdvanevery
Ryan Buchanan | ryan301@revature.net | 385-432-9281 | buchanan.ryan22@gmail.com | https://github.com/RyanLBuchanan
Samuel Kuhn | samuel685@revature.net | 210-683-5990 | kuhnsamuel2@gmail.com | https://github.com/skuhn002
Taylor Billingsley | taylor486@revature.net | (256)-698-4352 | Taylorb3139@gmail.com | https://github.com/SakuraYuna

## Standup
Name | Contact Info | Item | 2023-03-08 | 2023-03-09 | 2023-03-10 | Name | Item | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | Name | Item | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | Name | Item | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | Name | Item | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07
Jeff Janes | https://github.com/JeffJanes2023 | Yesterday’s work: | Planetary digest, data from a planet, choice of planets | Finished most layout found and setup planetary API | Layout finished; CSS 95% complete; API 100% complete | Jeff | Yesterday’s work: | Worked onand completed several challenges and trying to use GIT mor regularly | I worked on trailhead and took the quizzes I managed to finish all the badges he assigned and actually started a new badge for GIT | Worked on GIT badge on Trailhead and then studied for QC and worked on trello kanban board | Worked on dex and looked at the project spreadsheet and made some adjustments to the trello scrumban board I also worked on a few of the challenges | Worked Dex and use cases and did scrumban board | Jeff | Yesterday’s work: | Worked on DEX in class -- Worked on P1 items and made some adjustments to trello srumban board added use case numbers to boxes for easier identification and adjusted them so we could seewho is working on what added item numbers to project doc | Took quizzes and worked on badges after class worked in class on the user interface and the PDP assignments | worked on Badges and some objects in P1 reviewed revature docs and finished PDP went through QC | Worked on P1 managed to get a use case finished made sure all my pdp was up to date moved some bosex around on trello | 3 use cases finished and worked about 85%successfully building the flows up wroked on P1 use cases and worked on portfolio | Jeff | Yesterday’s work: | p1 study quizzes trello | practice for cert and finish quizzes | took quizzes, worked on P1, focus on force study, trello | finished use cases study for adm cert | Badges studying for cert getting set up for cert testing as far as camera and devices and all software required presentation prep | Jeff | Yesterday’s work: | took the quiz
| Email: jeff308 | Today’s work: |  | Fine tuning CSS bit of coding for the interesting facts section | Today I working on the last little bell to the site it is 100% functional and could be turned in as is but just trying to make it a bit better. |  | Today’s work: | Starting the SDLC on Project 1 take our quiz and answer some QC questions | Hopefully starting the SDLC on P1 and continuing on the GIT trailhead | trailhead head badges and dex 4 and trello board | continue with DEX and the project spread sheet and badges | continue with DEX and the project spread sheet and badges |  | Today’s work: | quizzes p1 | P1 P1 P1 badges | P1 P1 P1 Badges | P1 portfolio creation flows and badges | P1 Dex403 Badges PDP use cases |  | Today’s work: | quizzes | badges cert practice | quizzes, focus on force study, P1, cert reservation, presentation | quizzes, focus on force study, badges, presentation | studying presentation |  | Today’s work:
| Invited to - https://github.com/Firehawks-Revature | Roadblocks: | GitHub and VS Code config | Flex (CSS) is a bit new and need to figure out implementation | Sometimes the javascript errors are a bit nondescript and I have to try and figure them out as well |  | Roadblocks: | I found shortcoming with the source control in vscode and in the GIT there seemed to be a disconnect and it caused some delays could have been that I am just not totally comfortable with each tool yet | thinking about P1 | anxiety on the first QC and not knowing salesforce | No real roadblocks that I can really remember other than running out f time | never got a chance to get work on badges so time |  | Roadblocks: | time and communication | hoping we can turn 2FA on the playground so we can do the badge work | time | had an issue with flows and the p1 use case time | following along with flow creation was rough and time limitations |  | Roadblocks: | time use case | qty of thing this week time | doing better at time meanagement but still wish I had more time to manage | time | time |  | Roadblocks:
|  | Comments: |  |  |  |  | Comments: | [6 empty] | Comments: | [6 empty] | Comments: | [6 empty] | Comments:
Nicholas Kroeger | github.com/NRKroeger | Yesterday’s work: | Pics cats, petfinder API, specific pages with details | Implemented wireframe, general design of homepage | Finish CSS, setup github directory | Nick | Yesterday’s work: | Project presentation, light studying | Trailhead studying, html/css/js quizzes | 1:1, studying, QC, intro to DEX403 | Began work on 403/salesforce intro, finished required trailheads | Dex403/salesforce training, Brief use case analysis beginning | Nick | Yesterday’s work: | light studying, beginning to develop use cases, 403/ SF learning | Begginings of use case implementations, UI learning | Salescloud, servicecloud stuff, worked on security badge, QC | Back to dex 403, revising ERD (imcomplete), | Dex403/flow work, looking for missing objects etc, planned out use cases for P1 | Nick | Yesterday’s work: | Security badge, P1 stuff | A few use cases, some troubleshooting | Doing Use cases, study for cert | Finished Use cases, marginal studying | Finsish Project, debug use cases, Finish presentation | Nick | Yesterday’s work: | Security badge, P1 stuff | A few use cases, some troubleshooting | Doing Use cases, study for cert | Finished Use cases, marginal studying | Finsish Project, debug use cases, Finish presentation
| Invited to - https://github.com/Firehawks-Revature | Today’s work: |  | Complete home page, work on api implementation, make alt. pages | Complete API implementation, Use append/remove to reactively change information on page with JS |  | Today’s work: | Quizzing/progress reports | 1:1, QC studying, continue trailhead given time | Trailhead, dex403 training, maybe begin project 1, discuss project 1 | Begin design phase of P1, decide what parts to give to any given memeber, continue salesforce training | Continue use case analysis, 'sprint' retrospective |  | Today’s work: | Begin sprint, assign as many use cases as possible (be realistic) | QC? Continue learning SF, implement/review ERD | Security Superbadge, continue learning, port data to new owner | Continue 403, work on use cases, port new erd to lucid, portfolio meeting | Implement a few use cases, keep studying, Security superbadge, try to assist others |  | Today’s work: | P1 Stuff, if I finish P1, either begin pres prep, or do security badge | Figure out best solution to an issue, studying, Ideally finish use cases | finish use cases, cont studying | Study, prepare presentation | Present, study |  | Today’s work: | P1 Stuff, if I finish P1, either begin pres prep, or do security badge | Figure out best solution to an issue, studying, Ideally finish use cases | finish use cases, cont studying | Study, prepare presentation | Present, study
|  | Roadblocks: | Not knowing how to use the API | Figuring out API, re-doing finnicky code (box model not functioning as expected) | Uncomfortable with API and certain JS methods |  | Roadblocks: | Noon is no longer noon, DST as normal is dumb. Cannot find location of professionlism intro video. Have to leave a bit early today ~5:15-5:30 | unable to start p1 | do not know Salesforce yet to make any significant progress on p1 | N/A | This week's sprint was pretty sparse due to attempting to do so while in the beginning of learning SF |  | Roadblocks: | Slight frustrations implemeting use cases, want to confirm profiles won't remove needed permissions from HR group | Licences restrictions make working very frustrating | General stuff, none in particular | Licences issues, lookup relationships not appearing? (Maybe have a fix?) | flow issue 8-2/8-3, time management |  | Roadblocks: | Stuck on superbadge setting, ended up burning time I intended to use on P1, so fell behind | Unsure about solution choices | License issue to complete use case | Licences, decided to just bypass the issue w/ the sam account | Email issues |  | Roadblocks: | Stuck on superbadge setting, ended up burning time I intended to use on P1, so fell behind | Unsure about solution choices | License issue to complete use case | Licences, decided to just bypass the issue w/ the sam account | Email issues
|  | Comments: |  |  |  |  | Comments: | [6 empty] | Comments: | [6 empty] | Comments: | [6 empty] | Comments:
Parker Van Every | https://github.com/pdvanevery | Yesterday’s work: | Movie database, weather database with 7 day forecast | Worked on CSS "Golden" template, styling design | Achieved MVP for application (Succesfully API call, data display) | Parker | Yesterday’s work: | Completed P0, studied notes for QC | Worked on trailhead badges, studied for QC | Studied for QC, had QC, started DEX403 | Worked on Trailhead, Salesforce exercises for DEX403 | Studied Salesforce Notes, trailhead badge | Parker | Yesterday’s work: | Salesforce note studying | QC studying, Salesforce studying, security trailhead badge | QC, security badge progress, 403dex | 403dex, security badge, identified objects for use cases | 403dex | Parker | Yesterday’s work: | Stuck on use case(s), got stuck on security badge | completed some use cases, quizzes, studied for exam | completed use cases (have 1 left), studied | studied test, trailhead badges, practice test | p1, trailhead badge, studied for test | Parker | Yesterday’s work: | Stuck on use case(s), got stuck on security badge | completed some use cases, quizzes, studied for exam | completed use cases (have 1 left), studied | studied test, trailhead badges, practice test | p1, trailhead badge, studied for test
|  | Today’s work: |  | Implement video game API Complete HTML and JS code | Adding additional features such as more displayed data |  | Today’s work: | Complete quizzes, complete QC, complete video introduction | QC, study last week's content | Trailhead, DEX403, P1 progress | DEX403, P1 progress, possibly Trailhead | Study notes, trailhead badges, P1 work |  | Today’s work: | P1, quizzes, check PDP requirements, 403dex | QC, 403dex, P1 | 403dex, security badge, P1 | 403dex, security badge, P1 | 403dex, security badge, p1 |  | Today’s work: | P1, quizzes, loom | finish use cases, security badge, study | finish last use case and take practice test once outside of class | p1 presentation stuff, badges, practice test | p1 presentation, trailhead badge, |  | Today’s work: | P1, quizzes, loom | finish use cases, security badge, study | finish last use case and take practice test once outside of class | p1 presentation stuff, badges, practice test | p1 presentation, trailhead badge,
| Invited to - https://github.com/Firehawks-Revature | Roadblocks: | Time | Haven't yet settled on API, weather, video game | Indecisiveness and actually understanding what we learned and physically putting it into practice |  | Roadblocks: | lack of sunlight from timechange makes mornings rough | Confused some of terminology from last week's content | Need to progress in Salesforce | None | Confused on some SF terms still |  | Roadblocks: | time management with other job, need to set aside more time for this | None atm | Still getting feet wet with solo salesforce navigation |  | wifi kept going out then went out for the entire day so looking to make up lost time |  | Roadblocks: | Stuck on SF stuff, not enough time | IP range use case, wondering if can just demonstrate for one profile | need some clarification on last use case | need to do more badges | none atm |  | Roadblocks: | Stuck on SF stuff, not enough time | IP range use case, wondering if can just demonstrate for one profile | need some clarification on last use case | need to do more badges | none atm
|  | Comments: |  |  |  |  | Comments: | [6 empty] | Comments: | [6 empty] | Comments: | [6 empty] | Comments:
Samuel Kuhn | https://github.com/skuhn002 | Yesterday’s work: | Chemical elements, initial wireframe | I made my first API call to the periodic table API | Created an object for information to share about specific elements + images; Add event listener to element select box | Sam | Yesterday’s work: | Completing styling on P0 website; practicing QC questions in Lab | Assessments; Reading through Trailhead material – got to half-way through Salesforce Platform Basics | Work on Trailhead badges; QC; Start Kanban Board for P1 | Setup Amplifire Training Playground; Salesforce lessons 1 and 2 | Homework Exercise 4-6; Studied Salesforce Notes | Sam | Yesterday’s work: | Salesforce Notes; Choose one Use Case | Worked on Deep Analyzing First Use Case #6 | Worked with Jeff and Taylor on collecting objects for updating the ERD | Completed first use case – add certifications w/ Quick Action | Made my second use case | Sam | Yesterday’s work: | Completed all but one of my personal use cases; completed phase 1 | Finished last personal use case; completed mandatory team use case | Reviewed Missed ?s on 1st practice exam (ADM); created P1 presentation template | Reviewed Missed ?s on 2nd practice exam (ADM) | Organized the presentation; created all my presentation content; debugged 2 of my use cases that had broken | Sam | Yesterday’s work: | Completed all but one of my personal use cases; completed phase 1 | Finished last personal use case; completed mandatory team use case | Reviewed Missed ?s on 1st practice exam (ADM); created P1 presentation template | Reviewed Missed ?s on 2nd practice exam (ADM) | Organized the presentation; created all my presentation content; debugged 2 of my use cases that had broken
|  | Today’s work: |  | Today I am going to develop the structure for my HTML pages based off of my wireframing | Flex box style header, footer and main info; Further CSS styling |  | Today’s work: | Gather P1 requirements, analyze and begin P1 design; | QC; I really want to begin requirements gathering for P1 | Revise Kanban Board Structure; Get a shared Salesforce Org setup for P1 | Checkout ERD with Ryan | • Review the ERD with the Team Review use case analysis with Nick; Select my use cases; P1 Retrospective |  | Today’s work: | Take further notes on last weeks salesforce notes; Start first use case | Talk to team about how to update ERD | Making my first Use Case; Work on Super Badge; Review last weeks notes | Decide on + Work on another use case | Start on a 3rd use case, work on security super badge, study |  | Today’s work: | work on completing p1: last personal use case; mandatory team use case as well | Study Process Automation + Debugging; First Focus on Force attempt | Review 2nd practice exam results | Do presentation today; run a practice presentation today; trailhead badges | Present; Study for Cert Exam |  | Today’s work: | work on completing p1: last personal use case; mandatory team use case as well | Study Process Automation + Debugging; First Focus on Force attempt | Review 2nd practice exam results | Do presentation today; run a practice presentation today; trailhead badges | Present; Study for Cert Exam
| Invited to - https://github.com/Firehawks-Revature | Roadblocks: | Not knowing API request | None that I can see at this point | None at the moment |  | Roadblocks: | Had a bug with P0: not sure how to cleanly add elements on select element change event without duplicating elements on second select | Been occupied with assessments and required work – haven’t had time to dive into P1; Don’t have any information on P1 to begin gathering requirements | Co-ordinating P1 is difficult - it's a big project and there's a lot of us | Not clear on what the ERD will diagram/how to proceed with P1 before the ERD is done | What exactly is a tool in the context of use case analysis? Please give me a concrete example |  | Roadblocks: | none - just time | Our ERD is missing an important object – Certifications Held; ERD has unnecessary objects – Employee (should be User) | User object can’t be a Master – solved – use the Contact object in similar situations – specifically when the “worker” doesn’t need access to the salesforce org even if they work for the company | Couldn't pull up Price Book Entry as a Related Object in the Product Formula Builder - rendering prices on the product page | time |  | Roadblocks: | payment object can't take on approval process - solution: create a reimbursement object for approval | N/A | n/a | work overload | n/a |  | Roadblocks: | payment object can't take on approval process - solution: create a reimbursement object for approval | N/A | n/a | work overload | n/a
|  | Comments: |  |  |  |  | Comments: | [6 empty] | Comments: | [6 empty] | Comments: |  | I'd like to get started on the presentation slides for P1 by the end of day tomorrow |  |  |  |  | Comments: |  | I'd like to get started on the presentation slides for P1 by the end of day tomorrow
Taylor Billingsley | https://github.com/SakuraYuna | Yesterday’s work: | Abstract, galaxy of cupcakes, agile sdlc | Working on API, shows daily NASA photos, pulling an API key Used different API syntax than shared by Ethan | Working on project aesthetics, pulling an additional Futurama API for my second button, working on Syntax | Taylor | Yesterday’s work: | QC Prep, Working on coding challenges, RevaturePro review for Salesforce curriculum + previous material | Completed initial Week 1 HTML and CSS evaluations Begin intro Salesforce badges Prep for QCs | Worked with Jeff on the Trello Application's organization | Getting my Salesforce setup, acquainted with ERD, etc. | Worked on ERD with Ryan, doing homework exercises for sections 4-5 and 4-6, | Taylor | Yesterday’s work: | Studying for quizzes and checking PDP schedules, | Worked on ERD by adding some additional objects we may need in our project, worked on 2 users stories, PDP video + Quiz | Worked on finding objects for the ERD with Jeff and Sam; Worked on some of the user stories with Jeff; Checked some of the user stories that I have, QC sessions completed | Studying Salesforce UI content/practiced on Trailshead, analysis of user stories; Trello, overview of requirements for presentation | Work on Dex403 content, completed Super Security Trailshead badge, content review | Taylor | Yesterday’s work: | Working on use cases, studying for today's quizzes, looking over PDP requirements | the quizzes; a few use case | Solved use cases using method Ethan taught via cust objs; FoF Study Guide review (Obj Man.) & L.A.B. | Working on flow | Worked on project slides + notes | Taylor | Yesterday’s work: | Working on use cases, studying for today's quizzes, looking over PDP requirements | the quizzes; a few use case | Solved use cases using method Ethan taught via cust objs; FoF Study Guide review (Obj Man.) & L.A.B. | Working on flow | Worked on project slides + notes
| Invited to - https://github.com/Firehawks-Revature | Today’s work: |  | Implement fully functional APis and overall webiste refine | Work on flex box, add another image to the background, try to add additional API |  | Today’s work: | QC Assessment, Salesforce Material Reading/Workthrough, etc. | Traveling | Complete my last Salesforce badge, read Rev Pro's Salesforce information, | Working on coding challenges, RevPro information, Getting oriented with P1 | Completing coding challenges for this week, reviewing this week's Salesforce material, Getting acquainted with the Analysis, etc. |  | Today’s work: | Quiz work | Completing QCs and the Superbadge, studying for the material we covered yesterday, and reviewing material for today | Working on the superbadge, studying the content on Rev Pro and doing more practice with the Salesforce platform, doing the performance review with Ethan | Attend portfolio-creation session at 12:30 - 1:00 p.m. EST with Ethan and group; work on Superbadge, Study content for this week, work on Dex403 7-3 exercise (Firehawks) | Meet with Cognizant representatives, attend Salesforce lab, Github badge + look over Javascript for Salesforce badge |  | Today’s work: | Doing quizzes, completing Loom videos, working on more use cases | focus on force exams; seucrity badge; finish more use cases | Cert-Exam prep; Work for use cases/ start slide presentations; security badge/other badges; turning in user portfolio (Phase I) task | Work on Trailhead badges again | Do presentation; work more on Trailhead badges + FocusonForce |  | Today’s work: | Doing quizzes, completing Loom videos, working on more use cases | focus on force exams; seucrity badge; finish more use cases | Cert-Exam prep; Work for use cases/ start slide presentations; security badge/other badges; turning in user portfolio (Phase I) task | Work on Trailhead badges again | Do presentation; work more on Trailhead badges + FocusonForce
|  | Roadblocks: | GitHub, Git repo | Need to get the API working with 6 buttons | Adding API to all six buttons |  | Roadblocks: | N/A | Traveling | N/A | N/A | Coordinating this with today's schedule |  | Roadblocks: | Connectivity Issues | Roadblocks for today: Time | N/A | As usual, time | N/A |  | Roadblocks: | Workaround on this one use case's permission sets to give the user just enough access to fulfill their roles without giving too much | can't get case access for a user (Alexandra Atello) | Standard Platform License doesn't have access to the standard Case object, and permissions won't allow access unless the User License permits access to the object itself | Flow issues | Rescheduled Cert date |  | Roadblocks: | Workaround on this one use case's permission sets to give the user just enough access to fulfill their roles without giving too much | can't get case access for a user (Alexandra Atello) | Standard Platform License doesn't have access to the standard Case object, and permissions won't allow access unless the User License permits access to the object itself | Flow issues | Rescheduled Cert date
|  | Comments: |  |  |  |  | Comments: | [6 empty] | Comments: | [6 empty] | Comments: |  |  | Note: Standard column width will now be 300 |  |  |  | Comments: |  |  | Note: Standard column width will now be 300

## Standup Notes 2
Name | Contact Info | Item | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | Name | Item | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | Name | Item | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14
Jeff Janes | https://github.com/JeffJanes2023 | Yesterday’s work: | took admin exam | Joined APEX with VSCODE Going through Apex notes did 5 challenges PDP Badges | APEX Notes Cert badges p2 use cases | worked on challenges and badges went over SOSL finished portfolio phase 2 studied for cert | work on triggers and studied for cert and did some badges wroked on portfolio | Jeff Janes |  | worked on cert prep got more badges and picked out three use cases I thought I could do | did quizzes and then worked on what I needed to , worked on badges and focused on using both vscode and developer console | relaxing by the pool going out for dinner and watching the sunset |  |  | Jeff Janes
| Email: jeff308 | Today’s work: | badges retrospective new content pdp | QC APEX | portfolio pdp badges | workday stuff p2 badges apex triggers trello and ERD PDP | study for cert look at use cases an more badges |  | Today’s work: | visual force quizzes p2 | qc and a prep thing this morning at 8 | looking for a new position that needs a salesforce admin. Good luck and take care |  |  |  | Today’s work:
| https://github.com/Fire-Hawks-Amplifire-Revature | Roadblocks: | trail head issue resolved during night | No real roadblocks so far today | nothing really | not too much today | just moving forward |  | Roadblocks: | none | none really | need to get my admin cert lol |  |  |  | Roadblocks:
|  | Comments: | [6 empty] | Comments: |  |  | Sounds nice and relaxing, get lots of those Solar Rays! You'll 100% get your cert, I believe in you!, がんばって！ (Good luck in Japanese!) - Taylor |  |  |  | Comments:
Nicholas Kroeger | github.com/NRKroeger | Yesterday’s work: | Studying, Admin exam | Began Apex,various other things for pdp and such | Cont. Apex, SOQL intro, coding challenges, portfolio, QC | Study SOQL stuff, light project discussion | STudying, Apex triggers, mostly finished ERD
| https://github.com/Fire-Hawks-Amplifire-Revature | Today’s work: | Retrospective, intro to apex, probably do a few badges | QC, finish pdp, continue apex | Continue learning, trailhead, SOQL, marginal P2 work | More study, a bit more analysis of project | Finish Apex stuff, general studying
|  | Roadblocks: | N/A |  |  | N/a | N/a
|  | Comments: | [6 empty] | Comments: | [6 empty] | Comments:
Parker Van Every | https://github.com/pdvanevery | Yesterday’s work: | Took Cert Exam | Trailhead, apex, 1:1 | Trailhead, QC, apex | Trailhead, Apex | Trailhead, apex, | Parker Van Every | Yesterday’s work: | study apex, study qc, apex trailheads | study for qc, trailhead, p2 |  |  |  | Parker Van Every | Yesterday’s work:
|  | Today’s work: | Apex, 1:1, trailhead badges | QC, Trailhead, Apex | Trailhead, apex, maybe p2 | Trailhead, Apex, specifically Admin study module | Trailhead, apex, QC practice if have time |  | Today’s work: | quizzes, study apex, study qc, pdp | qc, badges, p2 |  |  |  |  | Today’s work:
| https://github.com/Fire-Hawks-Amplifire-Revature | Roadblocks: | N/A | still confusing apex classes and method syntax with javascript syntax | N/A | Might be doing badges at too slow a rate |  |  | Roadblocks: | none | need to get better at writing apex code |  |  |  |  | Roadblocks:
|  | Comments: | [6 empty] | Comments: | [6 empty] | Comments:
[8 empty] | Contact Info | Item | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | Name | Item | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21
Samuel Kuhn | https://github.com/skuhn002 | Yesterday’s work: | Took Cert Exam over the weekend; worked on portfolio phase 2; studied for QC; tried to complete Data Security Badge - almost halfway done | Continued Reading through Apex notes - still have 3 sections to read | Continued Reading through Apex notes - one section left to read | Finished reading through Apex notes; started on the ERD with Taylor; analyzed the rest of the use cases for P2 | Completed the ERD with Nick; worked on Apex Trigger challenges; Data Security Trailhead Badge; QC Mock question on Apex content | Samuel Kuhn | Yesterday’s work: | Tried to start Portfolio Phase 3; Did 1 use case | Prepared GitHub for P2; Started second use case | P2 use case; interview practice; portfolio phase 3 - still only have 2 roles/responsibilities; challenge 1 for visualforce | Completed second P2 use case; practiced some mock interview questions | Worked on Orders and Products visualforce use case; QC prep; interview prep; | Samuel Kuhn | Yesterday’s work: | Made more progress on visualforce use case over the weekend; practiced for QC and interview stuff | Worked on visualforce use case more | VF use case - progress on re-rendering, adding products | Completed VF use case on Orders and Products; first attempt at testing | Ran all but restricted user testing on my trigger use case
|  | Today’s work: | 1:1's with Ethan, start studying developer content | Read the last 3 sections on Intro to Apex notes | Read the last section of the Apex notes | figure out what to do next; work on ERD | Decide on one or more use cases for P2; work on one or more use cases for P2; work on Data Security Trailhead Badge |  | Today’s work: | Notes; prepare for the week | Interview Prep; P2 work | get help on P2 use case; get help on visualforce challenge 1 or reccomend another challenge for practice | Work on a visualforce P2 use case; Study some topics that are hard for me (SOQL, SOSL, Visualforce) with Trailhead | work on managing products in an order visualforce page |  | Today’s work: | Try to make more progress on my visualforce use case; continue general studying | More VF use case | VF use case - removing products | primary focus is to get through as much apex testing as possible; also want to do some initial work on the presentation - would like to get some direction from Nick on that | Error handling and testing VF pages
| https://github.com/Fire-Hawks-Amplifire-Revature | Roadblocks: | n/a | n/a | n/a | not sure what is the best use of time currently | n/a |  | Roadblocks: | Portfolio Phase 3 seems to have nothing we can complete before the deadline | Need some clarification on how to coordinate manifest | 1) getting stuck on thinking about how to bulkify apex trigger for use case #13 - reject unsimiilar email domains; main problem: struggling to keep a SOQL statement out of a loop - getting associated contacts for each triggerinng contact; 2) challenge 1 Visualforce can't get a URL parameter - do I need to use an experince site for this? | Just a little confused on how use case #20 is refering to pages and apps interchangeably | I'd like to know a little about what to expect for the PD1 cert exam; still stuck on trying to rerender after deleting an order - is this a requirement for the use case? |  | Roadblocks: | 2 things I figured out over the weekend that really confused me: 1) in an extension - controller.getRecords is a really useful method; 2) if you are trying to take input that isn't related to an SObject field, you need to use page docType="html-5.0" and an apex:input instead of an apex:inputField | Pricebook entry field on the order item is required but hidden | Got stuck on but figured out updating my list view - came down to requerying records for the list view object | My testing files don't show up in VS Code - not sure if I need some specific file structure - was able to work around this by just doing testing in the Developer console | Still a little confused on an example of something to test on a VF page
|  | Comments: | [6 empty] | Comments: | [6 empty] | Comments: |  |  |  | I would really like to learn how to step through my code using the Developer Console. I think this could drastically speed-up my debugging process - mainly to see the values of variables at different times in exectuion.
Taylor Billingsley | https://github.com/SakuraYuna | Yesterday’s work: | Doing Cert Exam | Set up with Apex | Trailhead Badges + RevPro Challenges | Work on Trailhead badges, Worked on ERD + Trello Board | Studied and did Apex challenges, Trailhead, etc. | Taylor Billingsley | Yesterday’s work: | Studying APEX, Working on Apex Database badges, Salesforce Badges, etc; Completed 2 Use Cases | Apex Trigger Trailhead badges, Salesforce Badges | Apex Trigger Study, Preparing Visual Studio to Pull & Push Code from Our Org, Analysis of Use Case #15 and #21, and #27 | Did some prep work before starting on my Flow use case with Trailhead, VS connected to org and isolated the manifest within comments | Worked on use case #15 (mostly complete); visual force study | Taylor Billingsley | Yesterday’s work: | Worked on visualforce pages (80% ready, just need to work out the delete function on their second pages) | Fixed my visualforce delete button, adjusting page redirect with Page Ref instead of outputLink | Uploaded one of the visualforce pages; made adjustments to the other one | Visualforce page ready, just needs testing and some design (fixed the amount of records that show, might add next buttons for each page) | Update the quick action button underneath contacts in order to add the Contact-Type; Maintenance of my visualforce pages
| https://github.com/Fire-Hawks-Amplifire-Revature | Today’s work: | Work on new material, Work on more Trailhead badges, retrospective, PDP, etc. | Find Trailhead badges for apex | Set Up Workday Portal; Work more on badges; learn new content | Do more work on ERD and study more Apex content; keep fresh on Salesforce content | Complete PDP assignment for today, look over SF content, |  | Today’s work: | Quizzes and working more on P2; More Salesforce Content Drilling | QCs (all day), Interview Prep session, More study/Project analysis | Worked on Portofilo Phase III, Do Work with VisualForce Pages; Practice more with Apex Triggers | Work more on the flow for use case #21 and study visualforce pages; review Salesforce content about classes and their methods | Finish up case #15, officical start to case #21 |  | Today’s work: | Quizzes, Loom videos, study with lightning components | QC, more content, style pages so they're appealing | Going to implement custom method next and previous button for each page | Going to work on LWC content and test code + styling; I want to create a static resource styling sheet for all of our use cases | Testing for pages, completing different use case if possible, working on in-line editing feature
|  | Roadblocks: | N/A | N/A | N/A | N/A | N/A |  | Roadblocks: | N/A | N/A | N/A | N/A | The custom notification recipient on use case #15, have to assign to system admin |  | Roadblocks: | Need to do wireframe? | My VS says no results when I push but most likely a quick fix | Need to adjust one Schema.SObject method I put in my code for security | N/A | N/A
[9 empty] | Comments: | [6 empty] | Comments: |  |  |  | Would like to hear comments about design: can be later
[8 empty] | Nicholas Kroeger | Yesterday’s work: | Trailhead, starting P2 | Quizzes Loom, trailhead badges, light studying | Studying, QC, Visualforce intro | 2 Use cases, PDP interview, visualforce | Wrked towards apex use case, studying, looked through lecture notes | Nicholas Kroeger | Yesterday’s work: | Wireframing VF page, STudying for QC/quizzes | Most of Base functionality for VF page, studyed for QC | Most of VF page is done, need delete function. | Completed all required non-testing Use cases | Presentation prep, review, etc
Links: | Notes for Material (Start Week 5) | https://github.com/Revature-Salesforce-Training/curriculum/tree/main/Week_5/Apex%20Best%20Practices | [6 empty] | Today’s work: | Quizzes 1:1/ videos, a bit more p2, studying | QC, SOSL studying, P2 use cases | Learn manifest, complete use cases 3+2,interview practice pdpd thing | Read through all LN, maybe get to Apex use case | BUg fixing and VF use case |  | Today’s work: | Study for QC, Quizzes, VF page | QC, last minutes studying, finish (?) VF page | Begin to look into testing for apex, finish VF page, portfolio again | Reformat every phone number in the database so that I don't have to fugure out how to include format into the valid rule. Begin prepping pres, | Finish testing, bit more review, begin designing slideshow
[9 empty] | Roadblocks: |  |  |  | Airport :( It's okay ;( - Taylor | REGEX for use case 2 and read only stuff for use case 12 |  | Roadblocks: | Didnt have enough time to actually start the code for my VF page | N/A |  | Stuff we learned yesterday a but confusing | bit unclear on running tests
| New Github Link | https://github.com/Fire-Hawks-Amplifire-Revature | [6 empty] | Comments: | [6 empty] | Comments:
| P2 Document Link | https://docs.google.com/spreadsheets/d/1vBvzJ8oHD9Yr08NvLPHH8nMSkvbndx9Q/edit?fbclid=IwAR3Czhi_UGXjzWsKcTY1nSVGt7uYMgJZv0m0VSAqtC6-oV_6pBhaT1rCsHo#gid=356299350
P1 Document Link
| Trello Board | https://trello.com/b/wvRNgkLd/amplifire-p2-project
ERD Link

## Sheet for Updating
Contact Info | Item | 2023-04-20
Samuel Kuhn | Yesterday’s work: | Completed VF use case on Orders and Products; first attempt at testing
| Today’s work: | primary focus is to get through as much apex testing as possible; also want to do some initial work on the presentation - would like to get some direction from Nick on that
| Roadblocks: | My testing files don't show up in VS Code - not sure if I need some specific file structure - was able to work around this by just doing testing in the Developer console
| Comments: | I would really like to learn how to step through my code using the Developer Console. I think this could drastically speed-up my debugging process - mainly to see the values of variables at different times in exectuion.
Taylor Billingsley | Yesterday’s work: | Visualforce page ready, just needs testing and some design (fixed the amount of records that show, might add next buttons for each page)
| Today’s work: | Going to work on LWC content and test code + styling; I want to create a static resource styling sheet for all of our use cases
| Roadblocks: | N/A
Nicholas Kroeger | Yesterday’s work: | Completed all required non-testing Use cases
| Today’s work: | Reformat every phone number in the database so that I don't have to fugure out how to include format into the valid rule. Begin prepping pres,
| Roadblocks: | Stuff we learned yesterday a but confusing

## Retrospectives P1
Names | Category | 2023-03-13 | 2023-03-17 | 2023-03-24 | P1-- 4/3
Jeff | Things you did well | Completed HTML CSS and JS course work with a wireframe and P0 | Did badges and P1 breakdown |  | I was able to get through more badges and the use cases
| Things you can Improve on | there are some more obscure terms and aspects of Javascript that I had not really seen before so I need to brush up on those | connecting the dots between the objects we need to use in P1and what we are learning in DEX |  | badge work breaking down use cases into the proper action in salesforce. Get more hands on in salesforce to become more familiar withwhat options are available on each screen
| Any unresolved user stories | Getting the API for the challenges to process correctly | linking the objects in project |  | processed the wrong activitiy for one of the use cases
| Velocity |  |  |  | 12
| Other comments | We built up our communication skills as a team to a point where we are becoming more productive |  |  | I think we need a bit more working together time actually working together on aspects of class
Nick | Things you did well | Completed CSS and organization, had a good idea of what I wanted for my website through wireframes | Feel good about using salesforce, User stories feel less daunting than |  | I think I was efficient in doing my use cases and was available to try to help troubleshoot other team members' use cases
| Things you can Improve on | Time management- implementation of APIs, had to use a very simple API due to lower understanding | Bonus trailhead badges, QC studying |  | Began prep for presentation a bit sooner for more organized format
| Any unresolved user stories | Technically none, but had to drop intended features due to time constraints | None assigned |  | None assigned to me, and the group exceeded 100 pts
| Velocity |  |  | 3 | 15
Other comments
Parker | Things you did well | Was successful in doing deep-dive during self-studying to figure out problems as well as fully learn concepts I was hazy on before | Successful in learning more about salesforce and using it, trailhead badges are coming along. Understanding more of the requirements for the P1 and know where to improve for studying |  | Used class time efficiently to tackle use cases, had no problems troubleshooting on my own
| Things you can Improve on | Took too long to choose API, need to balance other jobs with this one | Could be more proactive about studying. Need to balance 2nd job with revature so I dont hold down team or get behind in studying |  | I could be more available to help others with their use cases; I was too focused on my own
| Any unresolved user stories | No additional user stories unresolved but could have added more features | n/a |  | none
| Velocity |  |  |  | 12
Other comments
Sam | Things you did well | I quickly met the base requirements such as getting an API request | Leadership initiative: Pushed for the Kanban board early on; Set up the Salesforce TP early on | I figured out my first ever Salesforce use case; got comfortable implementing related lists | Pushed to structure the presentation; fixed 2 use cases which broke for unknown reasons
| Things you can Improve on | Following my SDLC steps closer, especially following my own wireframe | get working on user stories | Understanding access/security - it's difficult to think through when a field isn't showing up | Better integration of demonstrations into presentation; better data security practices
| Any unresolved user stories | Adding an element to the info section of my site without it duplicating on second select | n/a | Showing campaigns on related list for opportunities | n/a
| Velocity |  | n/a | 4 | 13
| Other comments |  |  | completed use cases: allow lead engineer to add certs, make certification records visible | We need to rehearse our presentations more thoroughly
Taylor | Things you did well | Implementing the API into the first three buttons for my HTML document | Ryan and I completed the ERD | Grasping service cloud and its associated features | I did well at implementing the use cases into the Salesforce platform
| Things you can Improve on | Flex-Box maneuvering: need to work on flex-box orientations for my document + webpage design | The current progress I have on the user stories | Working better with flows + getting more familiar with the debug logs | I need to work on the presentation of my information
| Any unresolved user stories | Adding additional API calls to the other three buttons of my HTML document | n/a | N/A | N/A
| Velocity |  |  | Approx. 8 | Approx. 14
Other comments
Firehawks/ team as a whole | Things you did well | - We collaborated well to each other to make sure every one had a functioning API - Completed HTML CSS and JS course work with a wireframe and P0 - Helping each other overcome issues, especially related to API Requests – big kudos to Jeff and Ryan; - Making big decisions earlier in the design process such as the API to use for P0 - Communication during our stand-ups was clear and focused - We were very comfortable collaborating even though we don't know each other well | - Improved communications a lot - Better understanding of overall requirements of Project 1 - More confident with user stories (size not so daunting) - Feel more intuitive with the Salesforce platform - Very good Scrumban board setup |  | Solid communication, decent collaborating and helping each other
| Things you can Improve on | - We could work on uploading more information to Trello this week - Made some design decisions and steps earlier | - Need to assign user stories - Even better communications and dedication to moving the team forward |  | Time management, presentation preparation and cohesiveness, Not beating our heads against a wall, using the resources we have
Any unresolved user stories
Velocity
Other comments

## Retrospectives P2
Names | Category | Week 1 (4/3 - 4/7) |  | Week 3 (4/17-4/21)
Jeff | Things you did well | used the tools more efficiently for studying and completed many challengesExposed to APEX and SOQL and SOSL and they seem pretty straight forward. I need to look at triggers a bit more
| Things you can Improve on | I need to learn more about the manifest so we do not clash with each other in the future and fine tune skills on SOSL
| Any unresolved user stories | none
| Velocity | none
Other comments
Nick | Things you did well | Made an ERD, so that we have a better foundation to start from | Completed what was apparently one of the hardest use cases, did decent studying | Quickly completed the testing for my trigger/trigger helper
| Things you can Improve on | Using flex time more efficiently | REGEX/ cutting losses and doing a use case in a non-ideal way that meets MVP | Bit slow and unfocused this week
| Any unresolved user stories | no | 23,sort of 2 | Testing visualforce page, contacts thing
| Velocity | 5/2.5 | 18 | 6
| Other comments |  | Ideally will complete 18 over the weekend, If i cant figure out regex for 2, just change all phone nunmbers to 10 digit non format | May convert visualforce extensions into custom controllers to assist with test development over the weekend, prepare for pres by monday for practice
Parker | Things you did well | Helped break down some of the use cases for content we are familiar with
| Things you can Improve on | Not familiar enough with new content
| Any unresolved user stories | 0
| Velocity | 0
| Other comments | haven't chosen all use cases yet, will make significantly more progress next week
Sam | Things you did well | Broke down the use cases well; utilized Schema Builder | Worked ahead on a few things, so I think I'm getting exposed to hard concepts early | Improved my testing and security in apex understanding a lot from the beginning of this week.
| Things you can Improve on | I don't have much familiarity with some tools like the lookup filter, which seem to be important to know for preparing to tackle new use cases - I could definitiely improve my familiarity with tools such as the lookup filter | Better understanding of controllers for sure; lost a lot of time to this | Improve Testing practices - be more specific/relevant in what I test
| Any unresolved user stories | 0 | Still not done with my visualforce use case - difficulty with managing orders | Testing, Error Handling, Pro/Con List for Deployment
| Velocity | 5 | 6 | 12
| Other comments | completed the ERD and got assigned use cases; didn't get assigned a use case for the last category yet |  | Completed VF use case (12 pts)
Taylor | Things you did well | Getting Adjusted to the new material; Setting up the Trello board for our work and identifying user stories that I can begin working on | Completed use case #15 with flows, and it's fully operational; updated use cases #15, #5, and #4 | Design of visualforce pages
| Things you can Improve on | Understanding the visualforce stories; getting started on these user stories, but hoping to improve my progress on them over the weekend | Visualforce page implementation | Custom controller manipulation
| Any unresolved user stories | 0 | Visualforce page use cases | Debug log use case
| Velocity | 6 | 6 | 12
| Other comments | (Velocity 6 because I plan on finishing 2 stories this weekend)
Firehawks/ team as a whole | Things you did well | Getting the pre-requisites for our project completed (ERD formatted, Trello set up, developing an approach to our apex uploads via VS, setting up our org)
| Things you can Improve on | Getting the user stories started
| Any unresolved user stories | N/A
| Velocity | 11
Other comments

## Retrospective Asks - SK
To ensure we can get through our required topics for the meeting please prepare the following to copy and paste into a shared document during the meeting:
user stories you accomplished so far
total story points you accomplished (since beginning P1)
if your name is on a completed user story with multiple people, include these story points as well
any specific roadblock you are facing (optional - if you don't have something specific, do not include this)
things you did well
things you can improve on
any user stories YOU have officially begun working on that are unresolved

## Archive
|  |  | 2023-03-08 | 2023-03-09 | 2023-03-10 |  |  | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17
Ryan Buchanan | https://github.com/RyanLBuchanan | Yesterday’s work: | Screaming Fire Kittens, detailed kitten page, kitten images | Completed draft (including wireframe, content, navigation, pages and assets) of initial cat website | Completed initial fully functional MVP. API request is working, have flexbox attribute on nav bar and JS event within the API request | Ryan | Yesterday’s work: | Completed Web dev code challenges for Week 1 (Wednesday) I - VII Created a Quizlet to help study for quizzes and QC questions | Completed initial Week 1 HTML and CSS evaluations Begin intro Salesforce badges Prep for QCs | Completed study for QC -> Passed QC Continued Trailhead study and badge training | Completed intro to Salesforce UI Began research for ERD development Complete review of Project 1 requirements and actionables Added to Trello board | Complete first draft of ERD Added documents to Firehawks GitHub repo Completed two chapters of Salesforce basic traiining
|  | Today’s work: |  | Implement API code for cat breeds Revise and complete website draft for submission as Project 0 | Review and revise Project 0 - code cleanup |  | Today’s work: | Complete quizzes Complete 1:1 evaluations | Continue Salesforce introductory badges Prep for QCs | Continue work on Salesforce introduction Begin work on Entity Relational Databases Refine Project 1 Trello board | Draft a ERD document - LucidChart Assign ERD objects rectangles Assign Analysis doc and begin drafting Compare tools/technology for P1??? | Review, revise and submit ERD (with Taylor) Update Firehawks GitHub repo with ERD and docs
| Admin - https://github.com/Firehawks-Revature | Roadblocks: | Time | Implementing API code for cat breeds | Still have question on API and event implementation |  | Roadblocks: | The scope of materials does seem a bit overwhelming. Found that coding challenges were taking more time than available so did not complete Thursday's | Nervousness and uncertainty with QCs Failed JS evaluations | None thus far | Communication channel needs refinement | Better communication channel needed - resolved during standup
|  | Comments: |  |  |  |  | Comments: