## Contacts
Name | Email | Phone | Personal email | GitHub
Jeff Janes | jeff308@revature.net | 925.699.7918 | jjanes0918@gmail.com | https://github.com/JeffJanes2023
Nicholas Kroeger | nicholas537@revature.net | (203) 917-5168 | nrkroeger1@gmail.com | github.com/NRKroeger
Parker Van Every | parker954@revature.net | (619) 750-4673 | pdvanevery@gmail.com | https://github.com/pdvanevery
Ryan Buchanan | ryan301@revature.net | 385-432-9281 | buchanan.ryan22@gmail.com | https://github.com/RyanLBuchanan
Samuel Kuhn | samuel685@revature.net | 210-683-5990 | kuhnsamuel2@gmail.com | https://github.com/skuhn002
Taylor Billingsley | taylor486@revature.net | (256)-698-4352 | Taylorb3139@gmail.com | https://github.com/SakuraYuna

## Standup
Name | Contact Info | Item | 2023-03-08 | 2023-03-09 | 2023-03-10 | Name | Item | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | Name | Item | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24
Jeff Janes | https://github.com/JeffJanes2023 | Yesterday’s work: | Planetary digest, data from a planet, choice of planets | Finished most layout found and setup planetary API | Layout finished; CSS 95% complete; API 100% complete | Jeff | Yesterday’s work: | Worked onand completed several challenges and trying to use GIT mor regularly | I worked on trailhead and took the quizzes I managed to finish all the badges he assigned and actually started a new badge for GIT | Worked on GIT badge on Trailhead and then studied for QC and worked on trello kanban board | Worked on dex and looked at the project spreadsheet and made some adjustments to the trello scrumban board I also worked on a few of the challenges | Worked Dex and use cases and did scrumban board | Jeff | Yesterday’s work: | Worked on DEX in class -- Worked on P1 items and made some adjustments to trello srumban board added use case numbers to boxes for easier identification and adjusted them so we could seewho is working on what added item numbers to project doc | Took quizzes and worked on badges after class worked in class on the user interface and the PDP assignments | worked on Badges and some objects in P1 reviewed revature docs and finished PDP went through QC | Worked on P1 managed to get a use case finished made sure all my pdp was up to date moved some bosex around on trello | 3 use cases finished and worked about 85%successfully building the flows up wroked on P1 use cases and worked on portfolio
| Email: jeff308 | Today’s work: |  | Fine tuning CSS bit of coding for the interesting facts section | Today I working on the last little bell to the site it is 100% functional and could be turned in as is but just trying to make it a bit better. |  | Today’s work: | Starting the SDLC on Project 1 take our quiz and answer some QC questions | Hopefully starting the SDLC on P1 and continuing on the GIT trailhead | trailhead head badges and dex 4 and trello board | continue with DEX and the project spread sheet and badges | continue with DEX and the project spread sheet and badges |  | Today’s work: | quizzes p1 | P1 P1 P1 badges | P1 P1 P1 Badges | P1 portfolio creation flows and badges | P1 Dex403 Badges PDP use cases
| Invited to - https://github.com/Firehawks-Revature | Roadblocks: | GitHub and VS Code config | Flex (CSS) is a bit new and need to figure out implementation | Sometimes the javascript errors are a bit nondescript and I have to try and figure them out as well |  | Roadblocks: | I found shortcoming with the source control in vscode and in the GIT there seemed to be a disconnect and it caused some delays could have been that I am just not totally comfortable with each tool yet | thinking about P1 | anxiety on the first QC and not knowing salesforce | No real roadblocks that I can really remember other than running out f time | never got a chance to get work on badges so time |  | Roadblocks: | time and communication | hoping we can turn 2FA on the playground so we can do the badge work | time | had an issue with flows and the p1 use case time | following along with flow creation was rough and time limitations
|  | Comments: |  |  |  |  | Comments: | [6 empty] | Comments:
Nicholas Kroeger | github.com/NRKroeger | Yesterday’s work: | Pics cats, petfinder API, specific pages with details | Implemented wireframe, general design of homepage | Finish CSS, setup github directory | Nick | Yesterday’s work: | Project presentation, light studying | Trailhead studying, html/css/js quizzes | 1:1, studying, QC, intro to DEX403 | Began work on 403/salesforce intro, finished required trailheads | Dex403/salesforce training, Brief use case analysis beginning | Nick | Yesterday’s work: | light studying, beginning to develop use cases, 403/ SF learning | Begginings of use case implementations, UI learning | Salescloud, servicecloud stuff, worked on security badge, QC | Back to dex 403, revising ERD (imcomplete), | Dex403/flow work, looking for missing objects etc, planned out use cases for P1
| Invited to - https://github.com/Firehawks-Revature | Today’s work: |  | Complete home page, work on api implementation, make alt. pages | Complete API implementation, Use append/remove to reactively change information on page with JS |  | Today’s work: | Quizzing/progress reports | 1:1, QC studying, continue trailhead given time | Trailhead, dex403 training, maybe begin project 1, discuss project 1 | Begin design phase of P1, decide what parts to give to any given memeber, continue salesforce training | Continue use case analysis, 'sprint' retrospective |  | Today’s work: | Begin sprint, assign as many use cases as possible (be realistic) | QC? Continue learning SF, implement/review ERD | Security Superbadge, continue learning, port data to new owner | Continue 403, work on use cases, port new erd to lucid, portfolio meeting | Implement a few use cases, keep studying, Security superbadge, try to assist others
|  | Roadblocks: | Not knowing how to use the API | Figuring out API, re-doing finnicky code (box model not functioning as expected) | Uncomfortable with API and certain JS methods |  | Roadblocks: | Noon is no longer noon, DST as normal is dumb. Cannot find location of professionlism intro video. Have to leave a bit early today ~5:15-5:30 | unable to start p1 | do not know Salesforce yet to make any significant progress on p1 | N/A | This week's sprint was pretty sparse due to attempting to do so while in the beginning of learning SF |  | Roadblocks: | Slight frustrations implemeting use cases, want to confirm profiles won't remove needed permissions from HR group | Licences restrictions make working very frustrating | General stuff, none in particular | Licences issues, lookup relationships not appearing? (Maybe have a fix?) | flow issue 8-2/8-3, time management
|  | Comments: |  |  |  |  | Comments: | [6 empty] | Comments:
Parker Van Every | https://github.com/pdvanevery | Yesterday’s work: | Movie database, weather database with 7 day forecast | Worked on CSS "Golden" template, styling design | Achieved MVP for application (Succesfully API call, data display) | Parker | Yesterday’s work: | Completed P0, studied notes for QC | Worked on trailhead badges, studied for QC | Studied for QC, had QC, started DEX403 | Worked on Trailhead, Salesforce exercises for DEX403 | Studied Salesforce Notes, trailhead badge | Parker | Yesterday’s work: | Salesforce note studying | QC studying, Salesforce studying, security trailhead badge | QC, security badge progress, 403dex | 403dex, security badge, identified objects for use cases | 403dex
|  | Today’s work: |  | Implement video game API Complete HTML and JS code | Adding additional features such as more displayed data |  | Today’s work: | Complete quizzes, complete QC, complete video introduction | QC, study last week's content | Trailhead, DEX403, P1 progress | DEX403, P1 progress, possibly Trailhead | Study notes, trailhead badges, P1 work |  | Today’s work: | P1, quizzes, check PDP requirements, 403dex | QC, 403dex, P1 | 403dex, security badge, P1 | 403dex, security badge, P1 | 403dex, security badge, p1
| Invited to - https://github.com/Firehawks-Revature | Roadblocks: | Time | Haven't yet settled on API, weather, video game | Indecisiveness and actually understanding what we learned and physically putting it into practice |  | Roadblocks: | lack of sunlight from timechange makes mornings rough | Confused some of terminology from last week's content | Need to progress in Salesforce | None | Confused on some SF terms still |  | Roadblocks: | time management with other job, need to set aside more time for this | None atm | Still getting feet wet with solo salesforce navigation |  | wifi kept going out then went out for the entire day so looking to make up lost time
|  | Comments: |  |  |  |  | Comments: | [6 empty] | Comments:
Samuel Kuhn | https://github.com/skuhn002 | Yesterday’s work: | Chemical elements, initial wireframe | I made my first API call to the periodic table API | Created an object for information to share about specific elements + images; Add event listener to element select box | Sam | Yesterday’s work: | Completing styling on P0 website; practicing QC questions in Lab | Assessments; Reading through Trailhead material – got to half-way through Salesforce Platform Basics | Work on Trailhead badges; QC; Start Kanban Board for P1 | Setup Amplifire Training Playground; Salesforce lessons 1 and 2 | Homework Exercise 4-6; Studied Salesforce Notes | Sam | Yesterday’s work: | Salesforce Notes; Choose one Use Case | Worked on Deep Analyzing First Use Case #6 | Worked with Jeff and Taylor on collecting objects for updating the ERD | Completed first use case – add certifications w/ Quick Action | Made my second use case
|  | Today’s work: |  | Today I am going to develop the structure for my HTML pages based off of my wireframing | Flex box style header, footer and main info; Further CSS styling |  | Today’s work: | Gather P1 requirements, analyze and begin P1 design; | QC; I really want to begin requirements gathering for P1 | Revise Kanban Board Structure; Get a shared Salesforce Org setup for P1 | Checkout ERD with Ryan | • Review the ERD with the Team Review use case analysis with Nick; Select my use cases; P1 Retrospective |  | Today’s work: | Take further notes on last weeks salesforce notes; Start first use case | Talk to team about how to update ERD | Making my first Use Case; Work on Super Badge; Review last weeks notes | Decide on + Work on another use case | Start on a 3rd use case, work on security super badge, study
| Invited to - https://github.com/Firehawks-Revature | Roadblocks: | Not knowing API request | None that I can see at this point | None at the moment |  | Roadblocks: | Had a bug with P0: not sure how to cleanly add elements on select element change event without duplicating elements on second select | Been occupied with assessments and required work – haven’t had time to dive into P1; Don’t have any information on P1 to begin gathering requirements | Co-ordinating P1 is difficult - it's a big project and there's a lot of us | Not clear on what the ERD will diagram/how to proceed with P1 before the ERD is done | What exactly is a tool in the context of use case analysis? Please give me a concrete example |  | Roadblocks: | none - just time | Our ERD is missing an important object – Certifications Held; ERD has unnecessary objects – Employee (should be User) | User object can’t be a Master – solved – use the Contact object in similar situations – specifically when the “worker” doesn’t need access to the salesforce org even if they work for the company | Couldn't pull up Price Book Entry as a Related Object in the Product Formula Builder - rendering prices on the product page | time
|  | Comments: |  |  |  |  | Comments: | [6 empty] | Comments:
Taylor Billingsley | https://github.com/SakuraYuna | Yesterday’s work: | Abstract, galaxy of cupcakes, agile sdlc | Working on API, shows daily NASA photos, pulling an API key Used different API syntax than shared by Ethan | Working on project aesthetics, pulling an additional Futurama API for my second button, working on Syntax | Taylor | Yesterday’s work: | QC Prep, Working on coding challenges, RevaturePro review for Salesforce curriculum + previous material | Completed initial Week 1 HTML and CSS evaluations Begin intro Salesforce badges Prep for QCs | Worked with Jeff on the Trello Application's organization | Getting my Salesforce setup, acquainted with ERD, etc. | Worked on ERD with Ryan, doing homework exercises for sections 4-5 and 4-6, | Taylor | Yesterday’s work: | Studying for quizzes and checking PDP schedules, | Worked on ERD by adding some additional objects we may need in our project, worked on 2 users stories, PDP video + Quiz | Worked on finding objects for the ERD with Jeff and Sam; Worked on some of the user stories with Jeff; Checked some of the user stories that I have, QC sessions completed | Studying Salesforce UI content/practiced on Trailshead, analysis of user stories; Trello, overview of requirements for presentation | Work on Dex403 content, completed Super Security Trailshead badge, content review
| Invited to - https://github.com/Firehawks-Revature | Today’s work: |  | Implement fully functional APis and overall webiste refine | Work on flex box, add another image to the background, try to add additional API |  | Today’s work: | QC Assessment, Salesforce Material Reading/Workthrough, etc. | Traveling | Complete my last Salesforce badge, read Rev Pro's Salesforce information, | Working on coding challenges, RevPro information, Getting oriented with P1 | Completing coding challenges for this week, reviewing this week's Salesforce material, Getting acquainted with the Analysis, etc. |  | Today’s work: | Quiz work | Completing QCs and the Superbadge, studying for the material we covered yesterday, and reviewing material for today | Working on the superbadge, studying the content on Rev Pro and doing more practice with the Salesforce platform, doing the performance review with Ethan | Attend portfolio-creation session at 12:30 - 1:00 p.m. EST with Ethan and group; work on Superbadge, Study content for this week, work on Dex403 7-3 exercise (Firehawks) | Meet with Cognizant representatives, attend Salesforce lab, Github badge + look over Javascript for Salesforce badge
|  | Roadblocks: | GitHub, Git repo | Need to get the API working with 6 buttons | Adding API to all six buttons |  | Roadblocks: | N/A | Traveling | N/A | N/A | Coordinating this with today's schedule |  | Roadblocks: | Connectivity Issues | Roadblocks for today: Time | N/A | As usual, time | N/A
|  | Comments: |  |  |  |  | Comments: | [6 empty] | Comments:

## Retrospectives
Names | Category | 2023-03-13 | 2023-03-17 | 2023-03-24
Jeff | Things you did well | Completed HTML CSS and JS course work with a wireframe and P0 | Did badges and P1 breakdown
| Things you can Improve on | there are some more obscure terms and aspects of Javascript that I had not really seen before so I need to brush up on those | connecting the dots between the objects we need to use in P1and what we are learning in DEX
| Any unresolved user stories | Getting the API for the challenges to process correctly | linking the objects in project
Velocity
| Other comments | We built up our communication skills as a team to a point where we are becoming more productive
Nick | Things you did well | Completed CSS and organization, had a good idea of what I wanted for my website through wireframes | Feel good about using salesforce, User stories feel less daunting than
| Things you can Improve on | Time management- implementation of APIs, had to use a very simple API due to lower understanding | Bonus trailhead badges, QC studying
| Any unresolved user stories | Technically none, but had to drop intended features due to time constraints | None assigned
Velocity
Other comments
Parker | Things you did well | Was successful in doing deep-dive during self-studying to figure out problems as well as fully learn concepts I was hazy on before | Successful in learning more about salesforce and using it, trailhead badges are coming along. Understanding more of the requirements for the P1 and know where to improve for studying
| Things you can Improve on | Took too long to choose API, need to balance other jobs with this one | Could be more proactive about studying. Need to balance 2nd job with revature so I dont hold down team or get behind in studying
| Any unresolved user stories | No additional user stories unresolved but could have added more features | n/a
Velocity
Other comments
Sam | Things you did well | I quickly met the base requirements such as getting an API request | Leadership initiative: Pushed for the Kanban board early on; Set up the Salesforce TP early on
| Things you can Improve on | Following my SDLC steps closer, especially following my own wireframe | get working on user stories
| Any unresolved user stories | Adding an element to the info section of my site without it duplicating on second select | n/a
Velocity
Other comments
Taylor | Things you did well | Implementing the API into the first three buttons for my HTML document | Ryan and I complete the ERD
| Things you can Improve on | Flex-Box maneuvering: need to work on flex-box orientations for my document + webpage design | The current progress I have on the user stories
| Any unresolved user stories | Adding additional API calls to the other three buttons of my HTML document | n/a
Velocity
Other comments
Firehawks/ team as a whole | Things you did well | - We collaborated well to each other to make sure every one had a functioning API - Completed HTML CSS and JS course work with a wireframe and P0 - Helping each other overcome issues, especially related to API Requests – big kudos to Jeff and Ryan; - Making big decisions earlier in the design process such as the API to use for P0 - Communication during our stand-ups was clear and focused - We were very comfortable collaborating even though we don't know each other well | - Improved communications a lot - Better understanding of overall requirements of Project 1 - More confident with user stories (size not so daunting) - Feel more intuitive with the Salesforce platform - Very good Scrumban board setup
| Things you can Improve on | - We could work on uploading more information to Trello this week - Made some design decisions and steps earlier | - Need to assign user stories - Even better communications and dedication to moving the team forward
Any unresolved user stories
Velocity
Other comments

## Retrospective Asks - SK
To ensure we can get through our required topics for the meeting please prepare the following to copy and paste into a shared document during the meeting:
user stories you accomplished so far
total story points you accomplished (since beginning P1)
if your name is on a completed user story with multiple people, include these story points as well
any specific roadblock you are facing (optional - if you don't have something specific, do not include this)
things you did well
things you can improve on
any user stories YOU have officially begun working on that are unresolved

## Archive
|  |  | 2023-03-08 | 2023-03-09 | 2023-03-10 |  |  | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17
Ryan Buchanan | https://github.com/RyanLBuchanan | Yesterday’s work: | Screaming Fire Kittens, detailed kitten page, kitten images | Completed draft (including wireframe, content, navigation, pages and assets) of initial cat website | Completed initial fully functional MVP. API request is working, have flexbox attribute on nav bar and JS event within the API request | Ryan | Yesterday’s work: | Completed Web dev code challenges for Week 1 (Wednesday) I - VII Created a Quizlet to help study for quizzes and QC questions | Completed initial Week 1 HTML and CSS evaluations Begin intro Salesforce badges Prep for QCs | Completed study for QC -> Passed QC Continued Trailhead study and badge training | Completed intro to Salesforce UI Began research for ERD development Complete review of Project 1 requirements and actionables Added to Trello board | Complete first draft of ERD Added documents to Firehawks GitHub repo Completed two chapters of Salesforce basic traiining
|  | Today’s work: |  | Implement API code for cat breeds Revise and complete website draft for submission as Project 0 | Review and revise Project 0 - code cleanup |  | Today’s work: | Complete quizzes Complete 1:1 evaluations | Continue Salesforce introductory badges Prep for QCs | Continue work on Salesforce introduction Begin work on Entity Relational Databases Refine Project 1 Trello board | Draft a ERD document - LucidChart Assign ERD objects rectangles Assign Analysis doc and begin drafting Compare tools/technology for P1??? | Review, revise and submit ERD (with Taylor) Update Firehawks GitHub repo with ERD and docs
| Admin - https://github.com/Firehawks-Revature | Roadblocks: | Time | Implementing API code for cat breeds | Still have question on API and event implementation |  | Roadblocks: | The scope of materials does seem a bit overwhelming. Found that coding challenges were taking more time than available so did not complete Thursday's | Nervousness and uncertainty with QCs Failed JS evaluations | None thus far | Communication channel needs refinement | Better communication channel needed - resolved during standup
|  | Comments: |  |  |  |  | Comments:

## Retrospective Archive-broken fo
Name | Item | 2023-03-13 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07
Jeff | Things you did well | Completed HTML CSS and JS course work with a wireframe and P0 | Did badges and P1 breakdown
| Things you can improve on | there are some more obscure terms and aspects of Javascript that I had not really seen before so I need to brush up on those | connecting the dots between the objects we need to use in P1and what we are learning in DEX
| Any user stories that are unresolved | Getting the API for the challenges to process correctly | linking the objects in project
| Velocity |  | 0
| Comments | We built up our communication skills as a team to a point where we are becoming more productive
Nick | Things you did well | Completed CSS and organization, had a good idea of what I wanted for my website through wireframes | Feel good about using salesforce, User stories feel less daunting than
| Things you can improve on | Time management- implementation of APIs, had to use a very simple API due to lower understanding | Bonus trailhead badges, QC studying
| Any user stories that are unresolved | Technically none, but had to drop intended features due to time constraints | None assigned
| Velocity |  | 5
Comments
Parker | Things you did well | Was successful in doing deep-dive during self-studying to figure out problems as well as fully learn concepts I was hazy on before | Successful in learning more about salesforce and using it, trailhead badges are coming along. Understanding more of the requirements for the P1 and know where to improve for studying
| Things you can improve on | Took too long to choose API, need to balance other jobs with this one | Could be more proactive about studying. Need to balance 2nd job with revature so I dont hold down team or get behind in studying
| Any user stories that are unresolved | No additional user stories unresolved but could have added more features | none
| Velocity |  | 0
Comments
Ryan | Things you did well | My KittyHub repo and VS Code project turned ou better than I expected | Completed first draft of ERD - very satisfactory ;) Great GitHUb organization and updating of materials Much improved communications - external channels working
| Things you can improve on | I really need some more practice on my JavaScript Need to form a better study stategy for quiz preparation Would like to get a better idea of QC question to improve prep | Definitely can improve communications My note taking could improve Need to improve QC study process
| Any user stories that are unresolved |  | Nope
| Velocity |  | 2.5
Comments
Sam | Things you did well | I quickly met the base requirements such as getting an API request | Leadership initiative: Pushed for the Kanban board early on; Set up the Salesforce TP early on
| Things you can improve on | Following my SDLC steps closer, especially following my own wireframe | get working on user stories
| Any user stories that are unresolved | Adding an element to the info section of my site without it duplicating on second select | n/a
| Velocity |  | 0
| Comments |  | user stories accomplished: none story points: 0
Taylor | Things you did well | Implementing the API into the first three buttons for my HTML document | Ryan and me complete the ERD
| Things you can improve on | Flex-Box maneuvering: need to work on flex-box orientations for my document + webpage design | The current progress I have on the user stories
| Any user stories that are unresolved | Adding additional API calls to the other three buttons of my HTML document | N/A
| Velocity |  | 2.5
| Comments | Things DoneWell: Communication during our stand-ups was clear and focused; Improvements: We could work on uploading more information to Trello this week
Firehawks | Things you did well | - We collaborated well to each other to make sure every one had a functioning API - Completed HTML CSS and JS course work with a wireframe and P0 - Helping each other overcome issues, especially related to API Requests – big kudos to Jeff and Ryan; - Making big decisions earlier in the design process such as the API to use for P0 - Communication during our stand-ups was clear and focused - We were very comfortable collaborating even though we don't know each other well | - Improved communications a lot - Better understanding of overall requirements of Project 1 - More confident with user stories (size not so daunting) - Feel more intuitive with the Salesforce platform - Very good Scrumban board setup
| Things you can improve on | - We could work on uploading more information to Trello this week - Made some design decisions and steps earlier | - Need to assign user stories - Even better communications and dedication to moving the team forward
Road blocks
| Velocity |  | 10 | 0 | 0 | 0